## Sheet1
04.05.2026 PS report on Project Cost details 1
| The Report is selected with Following Selection Criteria | [33 empty] | Report : |  | ZPSR0021A
| Projects From : | [14 empty] | To : | [18 empty] | Date/Time: |  | 04.05.2026 |  | / | 8:26
| Profit Centers From : | [7 empty] | 1687801 | [5 empty] | To : | [19 empty] | User : |  | 16807549
| Year / Period : | [8 empty] | 2026 |  | / | 5
Company Code |  |  |  |  | 168
Applicant no. | [5 empty] | 0 |  |  | -
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Project |  |  |  | 214687801/035 | [9 empty] | Alpha/T268 AMS FOR PIZZA LINE |  |  |  | Responsible Person |  |  | 70004679 | Alex Tan |  |  | Customer: | Alpha |  | Start Date: |  | 13.06.2014 |  | End Date: |  | 30.06.2024
214687801/035 | [10 empty] | Alpha/T268 AMS FOR PIZZA LINE | [5 empty] | 0 |  | 0 | 336538.8 |  | 840920.2 | 668384.8 | 1845843.7 |  |  | 0 |  | 0 |  | 9462600.3 |  | 0 |  |  | 9382675.5 |  | -7536831.8 |  |  | -9187331.1 | -9151569.1 | -9151569.1 | 0 | 231106.3
214687801/035-1 | [10 empty] | REWORK | [5 empty] | 119270.3 |  | 54060.2 | 113070.1 |  | 1414.4 | 57242.3 | 345057.2 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 345057.2 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-2 | [10 empty] | HANDLING OF CUSTOMERS' COMPLA | [5 empty] | 0 |  | 0 | 149806.8 |  | 0 | 0 | 149806.8 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 149806.8 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-3 | [10 empty] | ENTERTAINMENT EXPENSES | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-4 | [10 empty] | PROJECT ASSETS | [5 empty] | 33333 |  | 16912.9 | 0 |  | 0 | 15675 | 65920.9 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 65920.9 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-5 | [10 empty] | PRELIMINARY | [5 empty] | 922277 |  | 681702 | 2011.5 |  | 73543.1 | 73767.4 | 1753301 |  |  | 0 |  | 0 |  | 257942 |  | 0 |  |  | 0 |  | 1753301 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-6 | [10 empty] | PROJECT MANAGEMENT | [5 empty] | 150314.7 |  | 153687.3 | 3700.5 |  | 507157.9 | 721246 | 1536106.4 |  |  | 0 |  | 0 |  | 483509.5 |  | 0 |  |  | 0 |  | 1536106.4 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-7 | [10 empty] | SYSTEM DESIGN | [5 empty] | 0 |  | 0 | 24876.2 |  | 8096.2 | 0 | 32972.4 |  |  | 0 |  | 0 |  | 323000 |  | 0 |  |  | 0 |  | 32972.4 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-8 | [10 empty] | INSTALLATION DESIGN | [5 empty] | 0 |  | 0 | 32694.3 |  | 1986.6 | 3649 | 38329.8 |  |  | 0 |  | 0 |  | 1434542.4 |  | 0 |  |  | 0 |  | 38329.8 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-9 | [10 empty] | INSTALLATION AND CABLING WORK | [5 empty] | 0 |  | 0 | 787868.1 |  | 0 | 353300 | 1141168.1 |  |  | 0 |  | 0 |  | 1850000 |  | 0 |  |  | 0 |  | 1141168.1 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-10 | [10 empty] | IN-HOUSE SECURNET PRODUCT | [5 empty] | 0 |  | 0 | 122637.5 |  | 0 | 0 | 122637.5 |  |  | 0 |  | 0 |  | 1200000 |  | 0 |  |  | 0 |  | 122637.5 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-11 | [10 empty] | MANUFACTURING/PROCUREMENT | [5 empty] | 0 |  | 0 | 550807.1 |  | 844.2 | 121857.7 | 673509 |  |  | 0 |  | 0 |  | 600000 |  | 0 |  |  | 0 |  | 673509 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-12 | [10 empty] | IT NETWORK SECURITY | [5 empty] | 0 |  | 0 | 209050 |  | 0 | 71860 | 280910 |  |  | 0 |  | 0 |  | 300000 |  | 0 |  |  | 0 |  | 280910 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-13 | [10 empty] | CIVIL DEFENCE PROVISION | [5 empty] | 0 |  | 0 | 12276 |  | 0 | 12980 | 25256 |  |  | 0 |  | 0 |  | 60000 |  | 0 |  |  | 0 |  | 25256 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-14 | [10 empty] | EMC &TYPE TEST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 80750 | 80750 |  |  | 0 |  | 0 |  | 105000 |  | 0 |  |  | 0 |  | 80750 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-15 | [10 empty] | SYSTEM ASSURANCE (RAM) | [5 empty] | 0 |  | 0 | 0 |  | 0 | 31000 | 31000 |  |  | 0 |  | 0 |  | 86000 |  | 0 |  |  | 0 |  | 31000 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-16 | [10 empty] | SAFETY | [5 empty] | 0 |  | 0 | 2826 |  | 42.5 | 0 | 2868.5 |  |  | 0 |  | 0 |  | 246000 |  | 0 |  |  | 0 |  | 2868.5 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-17 | [10 empty] | SITE SUPERVISION | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 477500 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-18 | [10 empty] | DRAFTING SUPPORT | [5 empty] | 0 |  | 0 | 25218.3 |  | 77292.7 | 16594.5 | 119105.5 |  |  | 0 |  | 0 |  | 171000 |  | 0 |  |  | 0 |  | 119105.5 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-19 | [10 empty] | SITE TESTING & COMMISSIONING | [5 empty] | 0 |  | 0 | 0 |  | 0 | 97382.5 | 97382.5 |  |  | 0 |  | 0 |  | 850000 |  | 0 |  |  | 0 |  | 97382.5 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-20 | [10 empty] | PLANNING AND PRIMAVERA SUPPORT | [5 empty] | 0 |  | 0 | 0 |  | 0 | 23836.4 | 23836.4 |  |  | 0 |  | 0 |  | 72186 |  | 0 |  |  | 0 |  | 23836.4 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-21 | [10 empty] | ERROR IN CREATION | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-W | [10 empty] | DLP | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-22 | [10 empty] | TECHNICAL SUPPORT | [5 empty] | 80007.4 |  | 90222.8 | 189600 |  | 101375.7 | 9910.1 | 471116 |  |  | 0 |  | 0 |  | 200000 |  | 0 |  |  | 0 |  | 471116 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-23 | [10 empty] | VO | [5 empty] | 307732.3 |  | 105313 | 5616 |  | 0 | 5000 | 423661.3 |  |  | 0 |  | 0 |  | 523106.4 |  | 0 |  |  | 0 |  | 423661.3 |  |  | 0 | 0 | 0 | 0 | 0
214687801/035-24 | [10 empty] | NEW: IWR PLANNING SUPPORT | [5 empty] | 0 |  | 0 | 7497.2 |  | 100776.4 | 92704.1 | 200977.7 |  |  | 0 |  | 0 |  | 222814 |  | 0 |  |  | 0 |  | 200977.7 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214687801/035 | [13 empty] | 1612934.7 |  | 1101898.3 | 2576094.3 |  | 1713449.9 | 2457139.7 | 9461516.7 |  |  | 0 |  | 0 |  | 9462600.3 |  | 0 |  |  | 9382675.5 |  | 78841.2 |  |  | -9187331.1 | -9151569.1 | -9151569.1 | 0 | 231106.3
Totals: |  |  |  | 0 |  |  | - | [9 empty] | 1612934.7 |  | 1101898.3 | 2576094.3 |  | 1713449.9 | 2457139.7 | 9461516.7 |  |  | 0 |  | 0 |  | 9462600.3 |  | 0 |  |  | 9382675.5 |  | 78841.2 |  |  | -9187331.1 | -9151569.1 | -9151569.1 | 0 | 231106.3
Notes: Gross Profit = -ve
Gross Loss = +ve
Settlement: W = WIP (G/L 13500X)
R = R&D (G/L 736109)
O = Others (None of the above)
04.05.2026 PS report on Project Cost details 1
Applicant no. | [5 empty] | 87801009 |  |  | - |  | IMH/IVVRS FOR BetaMinistry
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Project |  |  |  | 183542967/021 | [9 empty] | IMH/IVVRS FOR BetaMinistry PHASE II |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 13.10.2016 |  | End Date: |  | 26.01.2021
183542967/021-1 | [10 empty] | IMH/IVVRS FOR BetaMinistry PHASE II | [5 empty] | 0 |  | 0 | 13792.4 |  | 52.6 | 3140 | 16985.1 |  |  | 0 |  | 0 |  | 4528626.4 |  | 1383.2 |  |  | 4527243.2 |  | -4510258.1 |  |  | -4922420 | -4922420 | -4922420 | 0 | -393793.6
183542967/021-1-1 | [10 empty] | REWORK | [5 empty] | 0 |  | 0 | 12257.7 |  | 1110.6 | 7346.5 | 20714.8 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 20714.8 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-2 | [10 empty] | HANDLING OF CUSTOMERS' COMPLAINTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-3 | [10 empty] | ENTERTAINMENT EXPENSES | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-4 | [10 empty] | PROJECT ASSETS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-5 | [10 empty] | PM & ENGINEERING | [5 empty] | 51381.8 |  | 62752.8 | 11532 |  | 8573 | 91775.5 | 226015 |  |  | 0 |  | 0 |  | 203501 |  | 0 |  |  | 0 |  | 226015 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-6 | [10 empty] | SUB-CON | [5 empty] | 0 |  | 0 | 2133 |  | 0 | 122715 | 124848 |  |  | 0 |  | 0 |  | 292395 |  | 0 |  |  | 0 |  | 124848 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-7 | [10 empty] | PH II SYSTEM EQUIPMENT + LICENSES | [5 empty] | 0 |  | 0 | 4080988.7 |  | 3735.6 | 53956 | 4138680.3 |  |  | 0 |  | 0 |  | 4032730.4 |  | 0 |  |  | 0 |  | 4138680.3 |  |  | 0 | 0 | 0 | 0 | 0
183542967/021-1-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 183542967/021 | [13 empty] | 51381.8 |  | 62752.8 | 4120703.8 |  | 13471.9 | 278933 | 4527243.2 |  |  | 0 |  | 0 |  | 4528626.4 |  | 1383.2 |  |  | 4527243.2 |  | 0 |  |  | -4922420 | -4922420 | -4922420 | 0 | -393793.6
Totals: |  |  |  | 87801009 |  |  | - | IMH/IVVRS FOR BetaMinistry | [8 empty] | 51381.8 |  | 62752.8 | 4120703.8 |  | 13471.9 | 278933 | 4527243.2 |  |  | 0 |  | 0 |  | 4528626.4 |  | 1383.2 |  |  | 4527243.2 |  | 0 |  |  | -4922420 | -4922420 | -4922420 | 0 | -393793.6
Notes: Gross Profit = -ve
Gross Loss = +ve
Settlement: W = WIP (G/L 13500X)
R = R&D (G/L 736109)
O = Others (None of the above)
04.05.2026 PS report on Project Cost details 1
Applicant no. | [5 empty] | 0 |  |  | -
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Project |  |  |  | 198346520/021 | [9 empty] | Alpha/CONTRACT T268A AMS FOR PIZZA STAGE 4 A |  |  |  | Responsible Person |  |  | 70004679 | Alex Tan |  |  | Customer: | Alpha |  | Start Date: |  | 28.09.2017 |  | End Date: |  | 28.08.2025
198346520/021-1 | [10 empty] | Alpha/CONTRACT T268A AMS FOR PIZZA STAGE 4 A | [5 empty] | 56252.7 |  | 11937.3 | 219174.9 | 0 | 404326.6 | 57449.3 | 749140.8 |  |  | 0 |  | 0 |  | 11327032.4 |  | 140009.7 |  |  | 10094626.2 |  | -9303677 |  |  | -9327101.7 | -8234705.2 | -8660952 | -426246.8 | 1999930.7
198346520/021-1-1 | [10 empty] | PRELIMINARY | [5 empty] | 25762.4 |  | 0 | 32844.3 | 0 | 105110.2 | 252357.6 | 416074.5 |  |  | 0 |  | 0 |  | 150000 |  | 0 |  |  | 0 |  | 1441579.3 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-2 | [10 empty] | PROJECT MANAGEMENT | [5 empty] | 0 |  | 1137767.3 | 8618.5 | 0 | 703913.5 | 0 | 1850299.3 |  |  | 0 |  | 0 |  | 2714736.3 |  | 0 |  |  | 0 |  | 613250 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-3 | [10 empty] | SYSTEM DESIGN | [5 empty] | 0 |  | 1024471.2 | 1175678.1 | 0 | 293278.9 | 28050 | 2521478.2 |  |  | 0 |  | 0 |  | 350000 |  | 0 |  |  | 0 |  | 88329.8 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-4 | [10 empty] | INSTALLATION DESIGN | [5 empty] | 1042223.7 |  | 992822.6 | 61456.1 | 0 | 15180 | 0 | 2111682.4 |  |  | 0 |  | 0 |  | 250000 |  | 0 |  |  | 0 |  | 234525.3 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-5 | [10 empty] | INSTALLATION AND CABLING WORK | [5 empty] | 5949.1 |  | 32148.5 | 19138.9 | 0 | 14081.9 | 1077642.5 | 1148960.9 |  |  | 0 |  | 6710 |  | 2577178.5 |  | 0 |  |  | 0 |  | 4324379 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-6 | [10 empty] | MANUFACTURING/HARDWARE | [5 empty] | 92784.7 |  | 90850.6 | 49486.6 | 0 | 189237.4 | 260713 | 683072.3 |  |  | 0 |  | 0 |  | 2500000 |  | 0 |  |  | 0 |  | 1625664 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-7 | [10 empty] | EMC & TYPE TEST | [5 empty] | 574857.7 |  | 0 | 14119.3 | 0 | 47202.6 | 677613.5 | 1313793.1 |  |  | 0 |  | 0 |  | 15000 |  | 0 |  |  | 0 |  | 93140 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-8 | [10 empty] | SYSTEM ASSURANCE (RAM) | [5 empty] | 148908 |  | 850622.2 | 13084.7 | 0 | 115685.4 | 274455.7 | 1402756 |  |  | 0 |  | 0 |  | 50000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-9 | [10 empty] | SITE SUPERVISION | [5 empty] | 11746.7 |  | 911431.6 | 0 | 0 | 0 | 31744.9 | 954923.2 |  |  | 0 |  | 0 |  | 150000 |  | 0 |  |  | 0 |  | 84489.1 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-10 | [10 empty] | DRAFTING SUPPORT | [5 empty] | 806592 |  | 0 | 49809.9 | 0 | 292769.6 | 313777.2 | 1462948.7 |  |  | 0 |  | 0 |  | 100000 |  | 0 |  |  | 0 |  | 169032.7 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-11 | [10 empty] | SITE TESTING & COMMISSIONING | [5 empty] | 220427.6 |  | 116706.3 | 77888 | 0 | 163430.9 | 1351023.5 | 1929476.3 |  |  | 0 |  | 54450 |  | 750000 |  | 0 |  |  | 0 |  | 208739.4 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-12 | [10 empty] | COST ALLOCATION | [5 empty] | 25528.7 |  | 45718.8 | 658133.7 | 0 | 202242.6 | 38363 | 969986.8 |  |  | 0 |  | 0 |  | 1720117.6 |  | 0 |  |  | 0 |  | 1512944.9 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-W | [10 empty] | DLP (18 MONTHS) | [5 empty] | 244656.6 |  | 50143 | 1954.4 | 0 | 1354466.3 | 669017 | 2320237.3 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
198346520/021-1-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 1436339.3 | 0 | 0 | 67303.1 | 1219001.3 | 2722643.7 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 198346520/021 | [13 empty] | 3255689.9 |  | 6700958.7 | 2381387.4 |  | 3968229 | 6251208.5 | 22557473.5 |  |  | 0 |  | 61160 |  | 11327032.4 |  | 140009.7 |  |  | 10094626.2 |  | 1092396.5 |  |  | -9327101.7 | -8234705.2 | -8660952 | -426246.8 | 1999930.7
Totals: |  |  |  | 0 |  |  | - | [9 empty] | 3255689.9 |  | 6700958.7 | 2381387.4 |  | 3968229 | 6251208.5 | 22557473.5 |  |  | 0 |  | 61160 |  | 11327032.4 |  | 140009.7 |  |  | 10094626.2 |  | 1092396.5 |  |  | -9327101.7 | -8234705.2 | -8660952 | -426246.8 | 1999930.7
Notes: Gross Profit = -ve
Gross Loss = +ve
Settlement: W = WIP (G/L 13500X)
R = R&D (G/L 736109)
O = Others (None of the above)
04.05.2026 PS report on Project Cost details 1
Applicant no. | [5 empty] | 83202015 |  |  | - |  | Alpha/C830G
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Project |  |  |  | 203451789/004 | [9 empty] | Alpha/C830G AMS |  |  |  | Responsible Person |  |  | 70003203 | Chris Yong |  |  | Customer: | Alpha |  | Start Date: |  | 12.12.2017 |  | End Date: |  | 30.06.2027
203451789/004-1 | [10 empty] | Alpha/C830G AMS | [5 empty] | 1061.08 |  | 259.94 | 60084.13 |  | 6195.6 | 0 | 67600.75 |  |  | 0 |  | 0 |  | 6827756 |  | 0 |  |  | 3952679.1 |  | -3875694.8 |  |  | -6827756 | -4093148.9 | -4093148.9 | 0 | -140469.7
203451789/004-1-1 | [10 empty] | SYSTEM DESIGN | [5 empty] | 1537957.07 |  | 610744.44 | 236612.29 |  | 121717.49 | 106535.5 | 2613566.79 |  |  | 0 |  | 0 |  | 2391642.5 |  | 0 |  |  | 0 |  | 2577647.1 |  |  | 0 | 0 | 0 | 0 | 0
203451789/004-1-2 | [10 empty] | MANUFACTURING/HARDWARE | [5 empty] | 1903.39 |  | 9047.65 | 544439.6 |  | 42226.77 | 253232.49 | 850849.9 |  |  | 996 |  | 280160 |  | 1588463.5 |  | 0 |  |  | 0 |  | 676917.4 |  |  | 0 | 0 | 0 | 0 | 0
203451789/004-1-3 | [10 empty] | SITE TESTING & COMMISSIONING | [5 empty] | 6634.45 |  | 2456.87 | 671338.07 |  | 635.95 | 399439.45 | 1080504.79 |  |  | 0 |  | 47400 |  | 1565583.4 |  | 0 |  |  | 0 |  | 1403525.3 |  |  | 0 | 0 | 0 | 0 | 0
203451789/004-1-4 | [10 empty] | V7 QDCU PRODUCTION | [5 empty] | 0 |  | 0 | 523941.91 |  | 0 | 924347.67 | 1448289.58 |  |  | 0 |  | 33535 |  | 1047750 |  | 0 |  |  | 0 |  | 1670109 |  |  | 0 | 0 | 0 | 0 | 0
203451789/004-1-W | [10 empty] | DLP | [5 empty] | 0 |  | 4276.79 | 49113.17 |  | 37285.11 | 5198.74 | 95873.81 |  |  | 0 |  | 0 |  | 234316.7 |  | 140469.7 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 140469.7
Total |  |  | 203451789/004 | [13 empty] | 1547555.99 |  | 626785.69 | 2085529.17 |  | 208060.92 | 1688753.85 | 6156685.62 |  |  | 996 |  | 361095 |  | 6827756 |  | 140469.7 |  |  | 3952679.1 |  | 2452504 |  |  | -6827756 | -4093148.9 | -4093148.9 | 0 | 0
Project |  |  |  | 203451789/004 | [9 empty] | Alpha/C830G AMS |  |  |  | Responsible Person |  |  | 70003203 | Chris Yong |  |  | Customer: | Alpha |  | Start Date: |  | 12.12.2017 |  | End Date: |  | 30.06.2027
203451789/004-2 | [10 empty] | VO | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 19700 |  | 19700 |  |  | 0 |  | 0 |  |  | -19700 | -19700 | -19700 | 0 | 0
203451789/004-2-1 | [10 empty] | VO COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 19700 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 203451789/004 | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 19700 |  | 19700 |  |  | 0 |  | 0 |  |  | -19700 | -19700 | -19700 | 0 | 0
Totals: |  |  |  | 83202015 |  |  | - | Alpha/C830G | [8 empty] | 1547555.99 |  | 626785.69 | 2085529.17 |  | 208060.92 | 1688753.85 | 6156685.62 |  |  | 996 |  | 361095 |  | 6847456 |  | 160169.7 |  |  | 3952679.1 |  | 2452504 |  |  | -6847456 | -4112848.9 | -4112848.9 | 0 | 0
Notes: Gross Profit = -ve
Gross Loss = +ve
Settlement: W = WIP (G/L 13500X)
R = R&D (G/L 736109)
O = Others (None of the above)
04.05.2026 PS report on Project Cost details 1
Applicant no. | [5 empty] | 0 |  |  | -
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-1 | [10 empty] | DESIGN AND DELIVERY OF 5 PREPRODUCTION | [5 empty] | 577.8 |  | 337.5 | 0 |  | 20424.6 | 0 | 21339.8 |  |  | 0 |  | 0 |  | 691371.3 |  | 68.1 |  |  | 691303.2 |  | -669963.4 |  |  | -768190.3 | -768190.3 | -768190.3 | 0 | -76819
214876532/FS/001-1-1 | [10 empty] | PM & ENGINEERING | [5 empty] | 164854.5 |  | 127515.8 | 5892.5 |  | 287246.4 | 64814.3 | 650323.5 |  |  | 0 |  | 0 |  | 551592.5 |  | 0 |  |  | 0 |  | 650323.5 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-1-2 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 0 |  | 0 | 19640 |  | 0 | 0 | 19640 |  |  | 0 |  | 0 |  | 139778.8 |  | 0 |  |  | 0 |  | 19640 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-1-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-1-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-1-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-1-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 165432.3 |  | 127853.2 | 25532.5 |  | 307671 | 64814.3 | 691303.3 |  |  | 0 |  | 0 |  | 691371.3 |  | 68.1 |  |  | 691303.2 |  | 0.1 |  |  | -768190.3 | -768190.3 | -768190.3 | 0 | -76819
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-2 | [10 empty] | BATCH 1 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 712644.2 |  | 2458.7 |  |  | 710185.6 |  | -710185.6 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
214876532/FS/001-2-1 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 35634 |  | 30167.4 | 619105 |  | 252.1 | 25027 | 710185.6 |  |  | 0 |  | 0 |  | 712644.2 |  | 0 |  |  | 0 |  | 710185.6 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-2-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-2-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-2-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-2-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 35634 |  | 30167.4 | 619105 |  | 252.1 | 25027 | 710185.6 |  |  | 0 |  | 0 |  | 712644.2 |  | 2458.7 |  |  | 710185.6 |  | 0 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-3 | [10 empty] | BATCH 2 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 712644.2 |  | 17258.5 |  |  | 695385.8 |  | -695385.8 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
214876532/FS/001-3-1 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 0 |  | 0 | 692650 |  | 2435.8 | 300 | 695385.8 |  |  | 0 |  | 0 |  | 712644.2 |  | 0 |  |  | 0 |  | 695385.8 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-3-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-3-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-3-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-3-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 692650 |  | 2435.8 | 300 | 695385.8 |  |  | 0 |  | 0 |  | 712644.2 |  | 17258.5 |  |  | 695385.8 |  | 0 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-4 | [10 empty] | BATCH 3 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 712644.2 |  | 4019.2 |  |  | 708625 |  | -708625 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
214876532/FS/001-4-1 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 0 |  | 0 | 700625 |  | 0 | 8000 | 708625 |  |  | 0 |  | 0 |  | 712644.2 |  | 0 |  |  | 0 |  | 708625 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-4-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-4-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-4-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-4-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 700625 |  | 0 | 8000 | 708625 |  |  | 0 |  | 0 |  | 712644.2 |  | 4019.2 |  |  | 708625 |  | 0 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-5 | [10 empty] | BATCH 4 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 712644.2 |  | 11756.1 |  |  | 700888.1 |  | -700888.1 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
214876532/FS/001-5-1 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 0 |  | 0 | 700625 |  | 263.1 | 0 | 700888.1 |  |  | 0 |  | 0 |  | 712644.2 |  | 0 |  |  | 0 |  | 700888.1 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-5-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-5-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-5-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-5-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
04.05.2026 PS report on Project Cost details 2
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 700625 |  | 263.1 | 0 | 700888.1 |  |  | 0 |  | 0 |  | 712644.2 |  | 11756.1 |  |  | 700888.1 |  | 0 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-6 | [10 empty] | BATCH 5 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 712644.2 |  | 56829.2 |  |  | 519243 |  | -519243 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -215754.7
214876532/FS/001-6-1 | [10 empty] | EQUIPMENT AND SOFTWARE | [5 empty] | 0 |  | 0 | 454954 |  | 17108 | 47181 | 519243 |  |  | 0 |  | 0 |  | 576072.2 |  | 0 |  |  | 0 |  | 519243 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-6-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 136572 |  | 0 | 0 | 136572 |  |  | 0 |  | 0 |  | 136572 |  | 0 |  |  | 136572 |  | 0 |  |  | 0 | 0 | 0 | 0 | 136572
214876532/FS/001-6-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-6-WN | [10 empty] | NON WARRANTY COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-6-WA | [10 empty] | ACCEPTED WARRANTY COSTS | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 591526 |  | 17108 | 47181 | 655815 |  |  | 0 |  | 0 |  | 712644.2 |  | 56829.2 |  |  | 655815 |  | 0 |  |  | -791826.9 | -791826.9 | -791826.9 | 0 | -79182.7
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-7 | [10 empty] | NEO 1 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-7-1 | [10 empty] | NEO 1 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-7-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-7-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-8 | [10 empty] | VA 1 AND VA 3 | [5 empty] | 0 |  | 0 | 5168488 |  | 0 | 0 | 5168488 |  |  | 0 |  | 0 |  | 9397699.2 |  | 643217.5 |  |  | 8754481.7 |  | -3585993.7 |  |  | -10441888 | -10441888 | -9919793.6 | 522094.4 | -1044188.8
214876532/FS/001-8-1 | [10 empty] | COSTING | [5 empty] | 976749.9 |  | 323847 | 1936469 |  | 278506.9 | 70421 | 3585993.7 |  |  | 0 |  | 0 |  | 9397699.2 |  | 0 |  |  | 0 |  | 3585993.7 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-8-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-8-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 976749.9 |  | 323847 | 7104957 |  | 278506.9 | 70421 | 8754481.7 |  |  | 0 |  | 0 |  | 9397699.2 |  | 643217.5 |  |  | 8754481.7 |  | 0 |  |  | -10441888 | -10441888 | -9919793.6 | 522094.4 | -1044188.8
Project |  |  |  | 214876532/FS/001 | [9 empty] | NG PROJECT |  |  |  | Responsible Person |  |  | 16808701 | Brian Wong |  |  | Customer: | Beta Ministry |  | Start Date: |  | 20.02.2019 |  | End Date: |  | 02.02.2029
214876532/FS/001-9 | [10 empty] | TP EV | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 559467 |  | 151340.3 |  |  | 305067 |  | -305067 |  |  | -621630 | -507119.2 | -481763.3 | 25355.9 | -50711.9
214876532/FS/001-9-1 | [10 empty] | PM | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 119467 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-9-2 | [10 empty] | HW / SW COST | [5 empty] | 0 |  | 0 | 291767 |  | 0 | 13300 | 305067 |  |  | 0 |  | 0 |  | 395000 |  | 0 |  |  | 0 |  | 305067 |  |  | 0 | 0 | 0 | 0 | 0
214876532/FS/001-9-3 | [10 empty] | HW SPARE | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 45000 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 214876532/FS/001 | [13 empty] | 0 |  | 0 | 291767 |  | 0 | 13300 | 305067 |  |  | 0 |  | 0 |  | 559467 |  | 151340.3 |  |  | 305067 |  | 0 |  |  | -621630 | -507119.2 | -481763.3 | 25355.9 | -50711.9
Project |  |  |  | 198234076/016 | [9 empty] | ABC FOR LINE |  |  |  | Responsible Person |  |  | 16809094 | David Ng |  |  | Customer: | Alpha |  | Start Date: |  | 16.07.2020 |  | End Date: |  | 30.03.2030
198234076/016-1 | [10 empty] | ABC FOR LINE | [5 empty] | 18239.9 |  | 13685.4 | 0 |  | 298880.2 | 0 | 330805.4 |  |  | 0 |  | 0 |  | 17093763.7 |  | 0 |  |  | 3601205 |  | -3270399.6 |  |  | -17093763.7 | -3620266 | -3921913.4 | -301647.4 | -19061
198234076/016-1-1 | [10 empty] | LABOUR | [5 empty] | 2314310.1 |  | 1389681.5 | 8460.5 |  | 843014.3 | 1509.1 | 4556975.6 |  |  | 0 |  | 0 |  | 4878338 |  | 0 |  |  | 0 |  | 4556975.6 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-2 | [10 empty] | MATERIAL | [5 empty] | 0 |  | 0 | 998633.9 |  | 3425.4 | 218688 | 1220747.3 |  |  | 0 |  | 43065 |  | 1932397.1 |  | 0 |  |  | 0 |  | 1220747.3 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-3 | [10 empty] | SUB-CON | [5 empty] | 7778 |  | 4837.5 | 1912000.2 |  | 76380.6 | 767686.9 | 2768683.2 |  |  | 0 |  | 144517.3 |  | 2906807 |  | 0 |  |  | 0 |  | 2768683.2 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-4 | [10 empty] | NEW: PRELIMS_PROJMGT | [5 empty] | 1075053.6 |  | 393270.3 | 1532.5 |  | 67811.4 | 73976.7 | 1611644.5 |  |  | 0 |  | 8400 |  | 1009393.8 |  | 0 |  |  | 0 |  | 1611644.5 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-5 | [10 empty] | NEW: FAT_STAGING | [5 empty] | 0 |  | 0 | 642 |  | 0 | 0 | 642 |  |  | 0 |  | 0 |  | 312600 |  | 0 |  |  | 0 |  | 642 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-6 | [10 empty] | NEW: INSTALLATION | [5 empty] | 0 |  | 0 | 151265.4 |  | 280.6 | 883835.6 | 1035381.6 |  |  | 0 |  | 928079.4 |  | 644000 |  | 0 |  |  | 0 |  | 1035381.6 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-7 | [10 empty] | NEW: STC_ITTC_TRAINING | [5 empty] | 0 |  | 0 | 0 |  | 0 | 3300 | 3300 |  |  | 0 |  | 0 |  | 929984.7 |  | 0 |  |  | 0 |  | 3300 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-8 | [10 empty] | NEW: ISMP (DEVELOPMENT) | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-9 | [10 empty] | NEW: ISMP (SECURNET HARDWARE) | [5 empty] | 0 |  | 0 | 162936.5 |  | 0 | 496479.5 | 659416 |  |  | 0 |  | 0 |  | 1249110.2 |  | 0 |  |  | 0 |  | 659416 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-10 | [10 empty] | NEW: ISMP (THIRDPARTY HARDWARE) | [5 empty] | 0 |  | 0 | 1385767.3 |  | 0 | 46345 | 1432112.3 |  |  | 0 |  | 408033.6 |  | 955573 |  | 0 |  |  | 0 |  | 1432112.3 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-11 | [10 empty] | NEW: ISMP (SUBCON INSTALLATION) | [5 empty] | 0 |  | 0 | 6246.4 |  | 0 | 472872.6 | 479119 |  |  | 0 |  | 265303.4 |  | 981129.5 |  | 0 |  |  | 0 |  | 479119 |  |  | 0 | 0 | 0 | 0 | 0
04.05.2026 PS report on Project Cost details 3
|  | Object | [8 empty] | Description | [5 empty] | LAB |  | FOH | MAT |  | Doc | SCO | Tot_Cost |  |  | Input Cost |  | COM_CST |  | PLAN_COS |  | COS-Prov |  |  | Cos/R&D |  | O/S WIP |  |  | QUOT_PR | REV | PB | O/S PB | Gr Profit
198234076/016-1-12 | [10 empty] | NEW: ISMP (SUBCON STC) | [5 empty] | 0 |  | 0 | 0 |  | 0 | 135576 | 135576 |  |  | 0 |  | 0 |  | 720000 |  | 0 |  |  | 0 |  | 135576 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-13 | [10 empty] | NEW: FIDS (LABOUR) | [5 empty] | 504430.7 |  | 189213.1 | 0 |  | 1619.7 | 0 | 695263.4 |  |  | 0 |  | 0 |  | 223660.5 |  | 0 |  |  | 0 |  | 695263.4 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-14 | [10 empty] | NEW: FIDS (MATERIALS) | [5 empty] | 0 |  | 0 | 74415.6 |  | -34100.2 | 7030.4 | 47345.8 |  |  | 0 |  | 2040 |  | 11950.6 |  | 0 |  |  | 0 |  | 47345.8 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-15 | [10 empty] | NEW: FIDS (SUBCON) | [5 empty] | 0 |  | 0 | 9071 |  | 43031.6 | 0 | 52102.6 |  |  | 0 |  | 145000 |  | 79109.9 |  | 0 |  |  | 0 |  | 52102.6 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-16 | [10 empty] | NEW: IWR PLANING SUPPORTING | [5 empty] | 0 |  | 0 | 0 |  | 75106.2 | 0 | 75106.2 |  |  | 0 |  | 0 |  | 169709.4 |  | 0 |  |  | 0 |  | 75106.2 |  |  | 0 | 0 | 0 | 0 | 0
198234076/016-1-W | [10 empty] | WARRANTY (18 MTHS) | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 90000 |  | 19061 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 19061
198234076/016-1-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 198234076/016 | [13 empty] | 3919812.3 |  | 1990687.7 | 4710971.3 |  | 1375449.7 | 3107299.9 | 15104220.9 |  |  | 0 |  | 1944438.7 |  | 17093763.7 |  | 19061 |  |  | 3601205 |  | 11503015.9 |  |  | -17093763.7 | -3620266 | -3921913.4 | -301647.4 | 0
Project |  |  |  | 207563841/003 | [9 empty] | STELS |  |  |  | Responsible Person |  |  | 30004178 | Edward Ngo |  |  | Customer: | Gamma Kinetics |  | Start Date: |  | 12.01.2021 |  | End Date: |  | 30.06.2024
207563841/003-1 | [10 empty] | STELS | [5 empty] | 24898.8 |  | 8503.3 | 10966.2 |  | 0 | 4860 | 49228.3 |  |  | 0 |  | 0 |  | 2248708 |  | 98732.7 |  |  | 2137975.3 |  | -2088747 |  |  | -2248708 | -2248708 | -2248708 | 0 | -12000
207563841/003-1-1 | [10 empty] | CCTV | [5 empty] | 794223.9 |  | 387714.8 | 0 |  | 0 | 1040 | 1182978.7 |  |  | 0 |  | 0 |  | 1121397.9 |  | 0 |  |  | 0 |  | 1182978.7 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-2 | [10 empty] | VISITOR MANAGEMENT SYSTEM | [5 empty] | 0 |  | 0 | 46055.2 |  | 129207.4 | 113050.6 | 288313.2 |  |  | 0 |  | 0 |  | 154162 |  | 0 |  |  | 0 |  | 288313.2 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-3 | [10 empty] | ACCESS CONTROL, INTRUSION DETECTION SYS | [5 empty] | 23946.5 |  | 7597 | 202513.5 |  | -7786.8 | 52220 | 278490.1 |  |  | 0 |  | 0 |  | 402461.1 |  | 0 |  |  | 0 |  | 278490.1 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-4 | [10 empty] | KMS | [5 empty] | 0 |  | 0 | 9920.1 |  | 0 | 0 | 9920.1 |  |  | 0 |  | 0 |  | 11076 |  | 0 |  |  | 0 |  | 9920.1 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-5 | [10 empty] | NEW SUB JOB - VO | [5 empty] | 0 |  | 0 | 16580.4 |  | 281461.5 | 13310 | 311351.9 |  |  | 0 |  | 0 |  | 522003 |  | 0 |  |  | 0 |  | 311351.9 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-6 | [10 empty] | VO FOR DATA CENTER | [5 empty] | 0 |  | 0 | 0 |  | 0 | 17693 | 17693 |  |  | 0 |  | 0 |  | 25608 |  | 0 |  |  | 0 |  | 17693 |  |  | 0 | 0 | 0 | 0 | 0
207563841/003-1-W | [10 empty] | WARRANTY | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 12000 |  | 12000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 12000
207563841/003-1-W-A | [10 empty] | WARRANTY ACCEPTED COST | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  |  | 207563841/003 | [13 empty] | 843069.2 |  | 403815.1 | 286035.3 |  | 402882.1 | 202173.6 | 2137975.3 |  |  | 0 |  | 0 |  | 2248708 |  | 110732.7 |  |  | 2137975.3 |  | 0 |  |  | -2248708 | -2248708 | -2248708 | 0 | 0
|  |  |  | 0 |  |  | - | [9 empty] | 5940697.6 |  | 2876370.4 | 15723794.1 |  | 2384568.7 | 3538516.7 | 30463947.7 |  |  | 0 |  | 1944438.7 |  | 33554230.2 |  | 1016741.3 |  |  | 18960931.7 |  | 11503016 |  |  | -35133314.5 | -21545306.2 | -21299503.1 | 245802.9 | -1567633.2
Notes: Gross Profit = -ve
Gross Loss = +ve
Settlement: W = WIP (G/L 13500X)
R = R&D (G/L 736109)
O = Others (None of the above)

## Sheet2
1578.2 | 336.3 | 382170.4 | 141305.9 | 265558.4 | 790949.2
744400.9 | 412660.8 | 154828.4 | 82313 | 47376.2 | 1441579.3
22166.1 | 8846.7 | 4179.9 | 263147.2 | 314910.2 | 613250
0 | 0 | 0 | 172.9 | 88156.9 | 88329.8
12668.8 | 11914.9 | 0 | 0 | 209941.7 | 234525.3
0 | 0 | 874655.6 | 4063.8 | 3445659.7 | 4324379
0 | 0 | 1256237.7 | 3361.9 | 366064.4 | 1625664
0 | 0 | 85540 | 0 | 7600 | 93140
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 84489.1 | 84489.1
0 | 0 | 58504.8 | 40416.1 | 70111.8 | 169032.7
0 | 0 | 0 | 17189.4 | 191550 | 208739.4
0 | 0 | 502204.4 | 222158.8 | 788581.7 | 1512944.9
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0
780814 | 433758.6 | 3318321.2 | 774128.9 | 5880000 | 11187022.7
780814 | 433758.6 | 3318321.2 | 774128.9 | 5880000 | 11187022.7