PROJECT FINANCIAL MANAGEMENT SYSTEM

Product Requirements Document

| Version | 1.1 — Updated with full tables and charts |
| --- | --- |
| Status | Draft — For Review |
| Author | James |
| Date | 18 May 2026 |
| Scope | Phase 1 — EAC, Resource Forecasting, AI Update Generation |
| Application | Standalone internal web application |
| Users | ~20 Project Managers + Project Directors + Department Leaders + Finance |

| 20 Project Managers | 5 User Roles | 3 Build Phases |
| --- | --- | --- |

# 1. Executive Summary

Project Managers across the organisation currently manage project financials in fragmented, inconsistent ways — relying on manual SAP exports, personal spreadsheets, and ad-hoc forecasting methods. Monthly reporting is a time-consuming burden with no standard format, resulting in inconsistent quality, late detection of cost overruns, and significant PMO overhead.

The Project Financial Management System (PFMS) is a dedicated internal web application that standardises EAC tracking, automates labour cost forecasting from headcount inputs, and uses AI to generate clear, professional project updates — removing the writing burden from Project Managers entirely.

Over time, the platform evolves into a Project Intelligence System — proactively surfacing risks, detecting anomalies, and prompting PMs before problems escalate.

## 1.1 Problem at a Glance

| Pain Point | Root Cause | Business Impact |
| --- | --- | --- |
| Late cost overrun detection | No real-time EAC tracking | Project losses, underbidding |
| Inconsistent PM reporting | No standard template or tool | Low comparability, audit risk |
| High PM admin time | SAP exports + manual spreadsheets | PM time wasted on admin vs delivery |
| Poor update quality | Freeform writing, variable English | Management cannot act on unclear updates |
| No portfolio visibility | Data siloed per PM | Management blind spots |
| Reactive forecasting | No forward-looking model | Surprises at project close |

# 2. Goals

| # | Goal | Description | Measure of Success |
| --- | --- | --- | --- |
| 1 | Reduce Admin Time | Cut time spent on monthly EAC updates, cost-to-complete calculations, and narrative project updates | Monthly update < 10 minutes |
| 2 | Reduce Inconsistency | Standardise wording, meaning, and writing style across all PMs regardless of English proficiency | Uniform structure across all updates |
| 3 | Encourage Timely Updates | Make reporting feel effortless so PMs submit on time without reminders or enforcement | > 90% on-time submission rate |
| 4 | Strategic — Intelligence | Evolve into a proactive Project Intelligence System that surfaces risks before they become problems | Phase 2 & 3 intelligence features adopted |

## 2.1 Out of Scope (Phase 1)

| Out of Scope | Planned For |
| --- | --- |
| Procurement and PO tracking | Phase 2 |
| Asset and licence lifecycle management | Phase 3 |
| Subcontractor billing reconciliation | Phase 3 |
| Client-facing portal | Not planned |
| Replacement of SAP as system of record | Not planned |

# 3. User Roles & Access

## 3.1 Role Hierarchy

System Admin Global access · User management · System configuration

▼

Department Leader All projects · Read-only · Portfolio oversight

▼

Project Director Own team's projects · Monitor PM compliance · Can also act as PM on own projects

▼

Project Manager Own projects only · Full edit · EAC + resource plan + AI updates

Finance —  Operates outside the project hierarchy. Dedicated SAP import access only. Cannot view project data or edit any project records.

## 3.2 Permission Matrix

| Permission | Sys Admin | Dept Leader | Proj Director | Proj Manager | Finance |
| --- | --- | --- | --- | --- | --- |
| View all projects (portfolio) | ✅ | ✅ | Own team only | Own only | ❌ |
| View project financials | ✅ | ✅ | ✅ | Own only | ❌ |
| Edit EAC / resource plan | ✅ | ❌ | Own projects only | ✅ | ❌ |
| Generate AI update | ✅ | ❌ | Own projects only | ✅ | ❌ |
| Upload SAP import | ✅ | ❌ | ❌ | ❌ | ✅ |
| Create / manage users | ✅ | ❌ | ❌ | ❌ | ❌ |
| Create projects | ✅ | ❌ | ❌ | ❌ | ❌ |
| Set role rates | ✅ | ❌ | ❌ | ❌ | TBC |
| View overdue report | ✅ | ✅ | Own team only | ❌ | ❌ |

# 4. Functional Requirements

## 4.1 EAC Tracking

### EAC Formula

| Component | Source | Description |
| --- | --- | --- |
| Actual Cost | SAP Import (auto) | Costs already incurred and booked in the financial system |
| Committed Cost | PM Input | Approved spend not yet delivered or invoiced |
| Labour Cost to Complete | System Calculated | Auto-calculated from future months in the resource plan |
| Other Cost to Complete | PM Input | Non-labour remaining costs entered by PM |
| = Cost to Complete | Labour CTC + Other CTC | Total estimated remaining spend |
| = EAC | Actual + Committed + CTC | Total projected cost at completion |
| Variance | Budget - EAC | Negative = over budget |

### Financial Health Indicators

| Status | Condition | Colour | Action Required |
| --- | --- | --- | --- |
| On Track | EAC within approved budget (variance ≥ 0%) | 🟢 Green | None — monitor |
| At Risk | EAC exceeds budget by up to 5% | 🟡 Amber | PM to explain and provide mitigation |
| Delayed | EAC exceeds budget by more than 5% | 🔴 Red | Escalation to Project Director |
| Completed | Project formally closed | 🔵 Blue | None |

### Time-Phased View

| Period | Past Months | Future Months |
| --- | --- | --- |
| Data Source | SAP actuals — auto-imported | Resource plan — system calculated |
| Editability | Read-only — locked | Editable by PM |
| Visual Style | Grey — historical | White — active forecast |
| Override | Not allowed | Allowed with mandatory explanation |

## 4.2 Resource & Labour Forecasting

| Feature | Description |
| --- | --- |
| Headcount Planning | PM selects role and number of people per month — no dollar entry required |
| Auto Cost Calculation | System multiplies headcount × daily rate × working days — PM never sees raw rates |
| Instant Recalculation | Any change to the resource plan immediately updates labour CTC and EAC |
| Working Calendar | Singapore public holidays pre-loaded — working days per month auto-calculated |
| Part-Time Support | Headcount supports decimals (e.g. 0.5 for half-time resources) |
| Copy Forward | PM can duplicate a monthly resource pattern to future months to reduce data entry |
| Past Month Lock | Past months are read-only — historical plan is preserved for audit |

## 4.3 AI-Assisted Project Update Generation

### How It Works

| Step | Action | Detail |
| --- | --- | --- |
| 1 | PM opens Update form | Selects phase, milestone, status, % complete, forecast date from dropdowns |
| 2 | Optional context | Short free-text field for specific details (e.g. '2 of 5 servers arrived') — max 500 characters |
| 3 | Click Generate | AI produces a 2–3 sentence professional update — text appears word by word in real time |
| 4 | Review | PM reads the output — regenerates if needed (usage tracked) |
| 5 | Confirm | PM confirms — update is saved as the official record for that month |

### Update Form Fields

| Field | Type | Options | Required? |
| --- | --- | --- | --- |
| Current Phase | Dropdown | Project phases defined at setup | Yes |
| Key Milestone | Dropdown | Milestones linked to selected phase | Yes |
| Overall Status | Button selector | On Track / At Risk / Delayed / Completed | Yes |
| % Complete | Number input | 0–100 | Yes |
| Original Forecast Date | Date picker | — | Yes |
| Revised Forecast Date | Date picker | — | If date changed |
| Issue / Risk | Dropdown | Vendor Delay / Client Approval / Resource Shortage / Scope Change / Technical Issue / etc. | No |
| Action Taken | Dropdown | Escalated / Expediting / Replanning / Additional Resources / etc. | No |
| Additional Context | Free text | Max 500 characters — point form acceptable | No |

## 4.4 SAP Data Import

| Feature | Description |
| --- | --- |
| Who Uploads | Finance team — dedicated role, not PMs |
| File Format | SAP Excel export — standard format, multiple sheets supported |
| Auto-Mapping | System maps rows to projects using WBS code lookup table |
| Unmapped WBS | Flagged in a review queue — Finance resolves by confirming the project mapping |
| Mapping Memory | Once a WBS code is mapped, remembered for all future uploads |
| Duplicate Detection | Same WBS code + period + amount in same batch is skipped |
| Import History | Every upload logged with timestamp, uploader, row counts, and status |

## 4.5 Dashboards

| Dashboard | Audience | Key Information |
| --- | --- | --- |
| Project Dashboard | Project Manager (own projects) | EAC, Budget, Variance, % Complete, Status indicator, Months Remaining, Cost trend chart, Resource plan, Update history |
| Portfolio Dashboard | Project Director, Department Leader, Admin | All projects table: Project, PM, Budget, EAC, Variance, Status, Last Updated, Overdue indicator — filterable, exportable to Excel |
| Compliance View | Project Director, Admin | Who has and has not submitted their monthly update — with days since last submission |

# 5. Project Intelligence Layer

Beyond storing and displaying data, PFMS is designed to act as a silent PMO analyst — watching patterns, surfacing risks, and prompting action at the right time. Intelligence features are built incrementally as the platform accumulates data.

Key Principle —  The system becomes smarter the longer it is used. Early adoption in Phase 1 creates the data foundation that powers intelligence in Phase 2 and 3.

| Intelligence Feature | What It Does | Phase | Data Needed |
| --- | --- | --- | --- |
| Slipping date detection | Alerts when revised forecast date keeps moving right month over month | 2 | 3+ months history |
| Stalled progress detection | Flags projects at risk for 3+ consecutive months with no % complete change | 2 | 3+ months history |
| Burn rate analysis | Compares actual spend rate vs % complete — surfaces optimistic forecasts | 2 | Actuals data |
| Anomaly detection | Flags unusual cost spikes or sudden % jumps requiring PM explanation | 2 | Actuals data |
| Milestone overdue alert | Notifies PM and PD when a milestone planned date has passed without completion | 2 | Milestone data |
| Mitigation suggestion library | Suggests common actions based on issue type, drawn from historical PM submissions | 3 | 6+ months history |
| Forecast accuracy scoring | Tracks each PM's forecast accuracy over time as a coaching and governance tool | 3 | 12+ months history |
| Predictive forecast dates | Suggests revised completion dates based on current burn rate and historical trend | 3 | 12+ months history |
| Portfolio risk surfacing | Auto-escalates at-risk projects to management view with supporting evidence | 3 | Multi-project data |

# 6. Phasing Plan

| Phase | Title | Features Included |
| --- | --- | --- |
| Phase 1 | Financial Foundation | • EAC calculation (Actual + Committed + CTC) • Time-phased view — past actuals vs future forecast • Resource and labour forecasting by headcount • AI-assisted project update generation (streaming) • SAP Excel import with WBS auto-mapping • Project dashboard + Portfolio dashboard • Monthly update compliance tracking • 5-tier RBAC (Admin, Dept Leader, PD, PM, Finance) |
| Phase 2 | Procurement & Intelligence | • PO and committed cost tracking • SAP real-time API integration • Delivery milestone tracking • Pattern recognition — slipping dates, stalled progress • Anomaly detection — cost spikes, % complete jumps • Milestone overdue alerts • Burn rate vs % complete analysis |
| Phase 3 | Full Project Ops Platform | • Asset and licence lifecycle management • Subcontractor tracking — PO vs billed amounts • Mitigation suggestion library • Forecast accuracy scoring per PM • Predictive forecast date suggestions • Site deployment and commissioning tracking • Portfolio risk auto-escalation |

# 7. Adoption Strategy

Core Principle —  If the tool feels like more work than a spreadsheet, adoption will fail. Every design decision must prioritise reducing PM effort first.

## 7.1 Rollout Timeline

| Period | Stage | Activity | Goal |
| --- | --- | --- | --- |
| Month 1–2 | Build | System development and internal testing | Working Phase 1 system |
| Month 3 | Pilot | 1–2 role model projects onboarded | Validate workflow, collect feedback |
| Month 4 | Refine | UX improvements based on pilot feedback | Remove friction before broad rollout |
| Month 5–6 | Soft Launch | All PMs onboarded with coaching sessions | Broad adoption begins |
| Month 7+ | Enforce | Mandatory adoption — linked to monthly review | Full compliance across team |

## 7.2 Change Management Principles

| Principle | How It Is Applied |
| --- | --- |
| Automate before asking | Everything that can be automated is automated — PMs only input what the system cannot derive |
| Management endorsement | EAC submissions linked to monthly project review agenda — non-submission is visible to leadership |
| Pilot first | 1–2 role model projects demonstrate the workflow before company-wide rollout |
| Coaching over enforcement | PMO runs monthly office hours during rollout — not just policy enforcement |
| Feedback loop | Monthly check-in with pilot PMs — issues resolved before broader adoption |

# 8. Infrastructure & Technology

| Component | Decision | Notes |
| --- | --- | --- |
| Hosting | Azure Virtual Machine (B4ms) | 4 vCPU, 16GB RAM — sized for full Phase 1 scope + Ollama |
| Estimated Cost | ~SGD $100–110/month | Auto-shutdown 1AM–7:30AM SGT saves ~25–30% on compute |
| Data Privacy | All data on company VM | No project data leaves the organisation's environment |
| AI Model | TBD — decision before build | Option A: Local model on VM (private). Option B: Cloud API (faster). |
| Database | PostgreSQL | Hosted on same VM |
| SAP Integration | Manual Excel upload (Phase 1) | Real-time API integration planned for Phase 2 |
| Users (Phase 1) | ~35–50 total users | 35 PMs + PDs + Dept Leaders + Finance + Admin |

## 8.1 AI Provider Options

| Factor | Option A: Local Model (Ollama) | Option B: Cloud API (Gemini Flash) |
| --- | --- | --- |
| Cost | Free — no API fees | Free tier — 1,500 requests/day |
| Data Privacy | ✅ Data stays on VM | ⚠️ Data sent to Google |
| Response Speed | 8–15s (CPU only, no GPU) | 1–3s |
| Setup Complexity | Moderate — Ollama install on VM | Simple — API key only |
| Output Quality | Good (3B model) | Very good |
| Concurrent Users | Queued (one at a time) | Parallel |
| Volume (our usage) | ~175 requests/month — fine | ~175 requests/month — 0.4% of daily limit |
| Decision | TBD | TBD |

# 9. Success Metrics

| Metric | Baseline Today | Target (6 months) | Measurement |
| --- | --- | --- | --- |
| % projects with up-to-date EAC | ~30% | > 90% | System compliance report |
| Time for PM monthly update | 1–3 hours | < 10 minutes | Time tracking in app |
| Late cost overrun detection (< 1 month to close) | Common | < 10% of projects | EAC variance trend |
| PMO manual consolidation time | High | Reduced by 70% | PMO self-reported |
| Update consistency (structure + tone) | Low — varies by PM | Uniform across all PMs | Qualitative review |
| PM satisfaction with reporting | Not measured | > 7/10 | Post-launch survey |

# 10. Open Questions

A full log of 100 questions is maintained in a separate document. The highest-priority items requiring decisions before build begins are listed below.

| # | Category | Question | Owner |
| --- | --- | --- | --- |
| 1 | SAP Import | What columns does the SAP Excel export contain? (sample file pending) | James / Finance |
| 2 | RBAC | Who manages role rates — Finance or System Admin? | Management |
| 3 | Reporting | Is there a fixed monthly submission date for PM updates? | PMO |
| 4 | AI | AI provider — local model (private) or cloud API (faster)? | James / IT |
| 5 | Finance | Can Finance view project financial data, or import access only? | Management |
| 6 | Technical | Is there an existing company SSO the app should integrate with? | IT |
| 7 | Data | Will historical project data need migration, or new projects only? | PMO |
| 8 | Reporting | Can you share the current slide template PMs use for monthly updates? | James |

— End of Document —   |   Version 1.1   |   18 May 2026